## Sheet1
Sprint 3. Plug in the Real Weather
days in sprint / effort left
Story ID | Story/task | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | 63 | 74 | 68 | 64 | 56 | 49 | 41 | 31 | 29 | 32 | 32 | 32 | 32 | 32
10 | Fetch one day temperature data from the weather provider system
| Make our server connect and authenticate to the provider system | 4 | 16 | 12 | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Read provider's data directory | 8 | 7 | 7 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Parse the current temperature out of the data | 6 | 6 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Push the temperature data to the client | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0
11 | Fetch rain, snow, etc details from the provider
| Parse snow/rain data from the provider's data | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Push the snow/rain data to the client | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
| Redesign client screen a bit | days in sprint / effort left 9: 3; days in sprint / effort left 10: 3; days in sprint / effort left 11: 3; days in sprint / effort left 12: 3; days in sprint / effort left 13: 3
| Refactor the server code | days in sprint / effort left 9: 4; days in sprint / effort left 10: 4; days in sprint / effort left 11: 4; days in sprint / effort left 12: 4; days in sprint / effort left 13: 4
12 | Fetch several days data from the provider
| Parse the weather data in day packs | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Push several days data to the client | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
13 | Auto-refresh feature
| Make the client ping server once per 4 hours | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| Make the server update the client | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Backlog state taken after day 9
based on: | http://agilesoftwaredevelopment.com/scrum/simple-sprint-backlog
Note on B6: Id of the story. To simplify linking to the product backlog
Note on C1: sprint goal
Note on C6: User story being implemented. See http://agilesoftwaredevelopment.com/scrum/simple-product-backlog
Note on C8: Task description are written in the language that team likes. It does not have to be management understandable or "correct". In this case the accurate description would be something like "Implement reading the provider's data directory on the server side", however, team decide to make it just "Read provider's data directory", because it was simpler and everybody on the team perfectly understood what this task was about
Note on C41: See for reference and comments. Feel free to remove the link, though it would be very kind of you to leave it somewhere on the sheet
Note on D10: The team tries not have tasks bigger, than 16 ideal engineering hours. If they happen to have a bigger task, they try to split it into two smaller and more managable ones
Note on E5: The formulae sums hundreds of cells. Just not to have to update the formulae when number of tasks changes significantly
Note on E7: The team underestimated the difficulties of connecting to the provider's CORBA server. Even though some work has been already done, the remaining amount is much bigger, than the original estimation for the whole task
Note on F20: Note formulae. It is convenient to copy the estimates automatically
Note on L15: After implementing some new code on the server side team realized that some refactoring would make the code better. The team could not predict it at the beginning of the sprint, therefore there were no estimates (nor the whole task) until day 9
Note on M5: Effort left went up after some new work has been discovered